## Read Me
UI / UX Build Effort Estimator
Draft v0.1 - starting values to be replaced with team experience-based hours
Purpose
What this is | A simple, explainable Excel reference for estimating the developer effort of modern web applications (UI plus the back-end APIs behind them) when responding to RFPs. A person reads the tables, picks the components and complexity, and the workbook totals the hours.
What it is not | Not a pricing tool, not a project plan, and not an estimator for agent / data-pipeline development. It only covers web UI and the API layer that serves it.
Who uses it
RFP / bid responder | Primary user (solution architect or tech lead). Turns RFP text into page and component counts. Works in the Estimator and How to choose sections.
Sales / pricing team | Reads the Estimator summary: total hours, person-days and indicative duration, with and without AI assistance.
Reviewers / leadership | Read the Complexity Rubric and Component Catalogue to confirm the definitions and hours are sensible.
UI and back-end developers | Maintain the numbers: enter experience-based hours in the Component Catalogue and Page Bundles, and log delivered projects in the Calibration log (Assumptions).
What the hours cover
Included | Developer build effort plus writing unit tests, for a typical first implementation by an average developer (not person-specific).
Excluded | UAT and integration testing, project management, requirements gathering, DevOps, database design, data pipelines, agent / RAG development.
Platform | Modern web apps only (Next.js / React baseline). No mobile or desktop applications.
How to use (5 steps)
1. Count pages | From the RFP, list the page types (login, dashboards, admin, etc.). Decide how many are Simple, Medium or Complex using the page definitions on the Page Templates sheet.
2. Enter pages | On the Estimator, type the counts into Section A. The hours per page come from the Page Templates sheet. Use the Page Explorer under Section A to see exactly which components make up any page and level.
3. Add shared / special components | In Section B pick extra components from the dropdown (app shell, navigation, Kanban board, pivot table, etc.), choose a complexity and enter a quantity.
4. Add backend APIs | In Section C enter how many endpoints of each type you expect. Use 'Typical API endpoints' on Page Templates as a guide.
5. Read the result | The summary at the top of the Estimator shows the total hours and person-days WITHOUT AI and WITH AI assistance. Review assumptions before quoting.
How to choose - RFP wording to inputs
"N login / sign-in screens" | Page type: Login & authentication page. Add Authentication endpoint in Section C.
"Dashboards / analytics views" | Page type: Dashboard / analytics page. Add Aggregation / analytics endpoints in Section C.
"Admin screens / user management" | Page type: Admin / configuration page. Add Role-based UI rendering in Section B and Authorisation layer in Section C.
"Search / list / master data screens" | Page type: List / search page, plus Detail / record page and Form / data-entry page for the record screens.
"Chatbot / assistant" | Page type: AI chat assistant page. Add an Agent / LLM-facing endpoint in Section C.
"Workflow / approval screens" | Page types: Wizard / guided workflow page and Agent / workflow monitor page.
"Reports / downloads" | Page type: Report & export page. Add Export / report endpoints in Section C.
"Integrates with N systems" | External system integration endpoint x N in Section C.
"SSO required" | Login page at Complex, Authentication endpoint at Complex, Role-based UI rendering in Section B.
"Kanban, pivot tables, tree views" | Not in any page template - add them individually in Section B.
Not sure about complexity | Use the Complexity Advisor sheet: pick the statement that fits for each dimension and it returns the level. Or use Medium by default (Complexity Rubric, Rule 2).
Sheet guide
Estimator | The only sheet most users need. Inputs and the final totals.
Summary | One-page view for sales and clients: headline totals, where the hours go, top page drivers, and a scenario comparison (baseline, current settings, what-if).
Complexity Advisor | Answer seven questions about a page or component and it recommends Simple, Medium or Complex using the rubric rules, with the reason and the hours.
Complexity Rubric | Generic rules for Simple / Medium / Complex.
Component Catalogue | Every UI and API component with Simple / Medium / Complex definitions, unit, and hours (without and with AI).
Page Templates | Page-level definitions and hours per page type and level. Calculated from Page Bundles.
Page Bundles | The component recipe behind each page template. Edit to tune a template.
Assumptions | AI-assist reduction (placeholder), technology factor, baseline assumptions and a calibration log.
Colour guide
Blue text on yellow | Input cell - safe to edit.
Black text | Formula or fixed text - do not overwrite.
Green / amber / red headers | Simple / Medium / Complex.
Important | Hours are DRAFT starting values for the team to replace with their experience-based figures, and the AI-assist reduction is a PLACEHOLDER. Review both before using the output in a customer bid.

## Estimator
UI / UX Build Effort Estimator
Enter counts in the blue cells. Sample inputs (1 login, 3 analytics, 4 admin pages) are pre-filled - overwrite them for your bid.
Project / RFP name | Sample project
Team size (used only for indicative duration) | 3
ESTIMATE SUMMARY | Without AI | With AI | Notes
A. UI pages (hours) |  |  | Pages from the page templates
B. Additional shared components (hours) |  |  | App shell, navigation and other individual components
C. Backend APIs (hours) |  |  | Endpoints and services
Technology factor |  |  | Set on the Assumptions sheet (1.00 = baseline stack)
TOTAL ESTIMATED EFFORT (hours) |  |  | Developer build + unit testing only. Excludes UAT, integration testing, PM and requirements gathering.
Person-days
Indicative duration (weeks, at team size above)
A. UI PAGES - enter page counts. Row total = #Simple x hrs + #Medium x hrs + #Complex x hrs (see Page Explorer below)
Page type | # Simple | # Medium | # Complex | Hrs per Simple page | Hrs per Medium page | Hrs per Complex page | Total hours (without AI)
Login & authentication page | 0 | 1 | 0
Dashboard / analytics page | 0 | 2 | 1
List / search page | 0 | 0 | 0
Detail / record page | 0 | 0 | 0
Form / data-entry page | 0 | 0 | 0
Wizard / guided workflow page | 0 | 0 | 0
Admin / configuration page | 1 | 2 | 1
AI chat assistant page | 0 | 0 | 0
Agent / workflow monitor page | 0 | 0 | 0
Report & export page | 0 | 0 | 0
Content / landing page | 0 | 0 | 0
Total - UI pages
PAGE EXPLORER - pick a page type and level to see exactly which components make up its hours
Page type (choose) | Login & authentication page |  |  | Level (choose) | Medium
What this level means
Component in this page | Level | Qty | Hrs each | Hours | What this level of the component looks like
Hours for ONE page of this type and level
B. ADDITIONAL SHARED COMPONENTS - pick from the catalogue (app shell, navigation, individual widgets, etc.)
Component (pick from list) | Complexity | Quantity | Layer | Hrs per unit | Total hours (without AI) | Unit
App shell & routing | Medium | 1
Sidebar navigation | Medium | 1
Top header / app bar | Medium | 1
Theme & design tokens | Simple | 1
Toast, alert & banner notifications | Medium | 1
Role-based UI rendering | Medium | 1
Session handling | Medium | 1
Total - additional components
C. BACKEND APIs - enter how many endpoints / services of each type and complexity
API type | # Simple | # Medium | # Complex | Hrs per Simple | Hrs per Medium | Hrs per Complex | Total hours (without AI)
CRUD endpoint | 0 | 6 | 0
List / search endpoint | 2 | 3 | 0
Aggregation / analytics endpoint | 0 | 2 | 1
Authentication endpoint | 0 | 1 | 0
Authorisation / RBAC layer | 0 | 1 | 0
File upload / download endpoint | 0 | 0 | 0
External system integration endpoint | 0 | 0 | 0
Real-time endpoint (SSE / WebSocket) | 0 | 0 | 0
Export / report endpoint | 0 | 0 | 0
Agent / LLM-facing endpoint | 0 | 0 | 0
Total - backend APIs

## Summary
Summary & Scenarios
One-page view for sales and clients. Everything here is calculated from the Estimator - no inputs except the yellow what-if cells.
Project / RFP
Headline | Without AI | With AI | Notes
Total effort (hours) |  |  | Developer build + unit testing
Person-days
Indicative duration (weeks)
Where the hours go
Area | Hours (without AI) | Hours (with AI) | Share of total
UI pages
Additional shared components
Backend APIs
Technology factor adjustment
Total
Top 5 UI page drivers
Page type (ranked by hours) | Hours (without AI) | Share of UI hours | # Simple / Medium / Complex
Scenario comparison (same scope, different assumptions)
| Baseline | Current settings | What-if (edit)
Meaning | No AI, baseline stack | Values on the Assumptions sheet | Your own values
Technology factor | 1 |  | 1.25
AI-assist reduction | 0% |  | 30%
Total hours
Person-days
Indicative weeks
Difference vs baseline
Scenarios use the same scope as the Estimator. Total = (pages + shared components + APIs) x technology factor x (1 - AI reduction).

## Complexity Advisor
Complexity Advisor - which level is it?
For each dimension pick the statement that best describes the item. The result follows the rubric rules: highest trigger wins, default to Medium.
Item being assessed | Sales performance dashboard
Page type (to show hours) | Dashboard / analytics page
Step 1 - for each dimension pick the statement that fits best (leave blank if it does not apply)
Dimension | Pick the statement that fits | Level | Score
Data source | Live data (polling, websocket) or chained / dependent API calls
Interaction | Sort, filter, select, open modals, submit forms
States & validation | Field validation, success and error states, server-error mapping
Component reuse | Library component with moderate customisation
Layout & responsiveness | Adapts to tablet and mobile widths
Permissions | Show or hide elements by role
Volume of data | Hundreds of rows, paginated
Step 2 - result
Dimensions answered
Recommended level
Why
Hours for ONE such page (without AI)
What to enter on the Estimator
The Advisor does not change the Estimator by itself. It tells you which level to use, so two estimators reading the same requirement reach the same answer.

## Complexity Rubric
Complexity Rubric - what Simple, Medium and Complex mean
Generic rules for classifying any component. Component-specific definitions are in the Component Catalogue.
Dimension | SIMPLE | MEDIUM | COMPLEX
Data source | Static / hard-coded data, or a single API call on page load | Several API calls, or one call with server-side paging, sorting or filtering | Live data (polling, websocket) or chained / dependent API calls
Interaction | Display only; basic click or navigation | Sort, filter, select, open modals, submit forms | Drag-and-drop, inline editing, real-time updates, keyboard shortcuts
States & validation | Default, loading and empty states | Field validation, success and error states, server-error mapping | Conditional or dependent fields, autosave, optimistic updates, partial failures
Component reuse | Used as-is from the component library | Library component with moderate customisation | Substantial custom component or custom rendering
Layout & responsiveness | Single fixed layout | Adapts to tablet and mobile widths | Dense multi-panel layout with reflow and sticky regions
Permissions | None | Show or hide elements by role | Field-level or dynamic permissions
Volume of data | Handful of rows or items | Hundreds of rows, paginated | Thousands of rows or very large payloads (virtualisation)
How to choose a level
Rule 1 - highest trigger wins | Pick the highest level for which ANY one trigger in the table applies. A component that needs live data is Complex even if everything else is simple.
Rule 2 - when unsure | Use Medium as the default. Use Complex for analytics-heavy or real-time screens.
Rule 3 - use component definitions | The Component Catalogue gives a concrete Simple / Medium / Complex description for every component. Where it exists, it overrides this generic rubric.
Rule 4 - hours scale | Hours are for one component, build plus unit test. As a calibration check, Medium is typically about 2x Simple and Complex about 2x Medium.
Example - data table | Simple: static columns loaded once from one API (4 h). Medium: server-side sort, filter and pagination (12 h). Complex: live updates, virtualisation, inline actions (24 h).

## Component Catalogue
Component Catalogue
Generic UI and back-end API components with complexity definitions and effort (developer build + unit test). Edit the blue hours; 'with AI' hours are calculated.
[7 empty] | Hours WITHOUT AI |  |  | Hours WITH AI (calculated)
Category | Layer | Component | Unit | Simple looks like | Medium looks like | Complex looks like | Simple | Medium | Complex | Simple | Medium | Complex
Foundation & Layout | UI | App shell & routing | per application | Header + content area, up to 3 static routes | Header + sidebar, route guards, 404/error pages | Multiple layouts (public/auth/admin), nested routes, global state, error boundaries | 8 | 16 | 32
Foundation & Layout | UI | Sidebar navigation | per application | Flat list of links | Grouped links, active state, collapsible | Multi-level nested menu, role-driven items, persisted state | 4 | 8 | 16
Foundation & Layout | UI | Top header / app bar | per application | Title and static links | Logo, user menu, notification badge | Global search, context/organisation switcher, notification dropdown | 3 | 6 | 12
Foundation & Layout | UI | Breadcrumbs & tabs | per page | Static breadcrumbs or tabs | Route-driven tabs and breadcrumbs | Data-driven breadcrumbs, guarded or lazy-loaded tabs | 2 | 4 | 8
Foundation & Layout | UI | Responsive layout | per page | Library grid, 2 breakpoints | Desktop / tablet / mobile adaptation of one page | Reflowing panels, collapsing regions, sticky areas on dense pages | 4 | 8 | 16
Foundation & Layout | UI | Master-detail view | per view | List + detail pane, static data | API-fed list and detail with synced selection | Editable detail, pagination, deep links, unsaved-changes guard | 8 | 16 | 28
Foundation & Layout | UI | Theme & design tokens | per application | Component-library theme with brand colours | Light/dark toggle, persisted preference | Custom design-system tokens, multiple brands/themes | 4 | 12 | 24
Foundation & Layout | UI | Static content section | per section | Text and images (e.g. footer, info block) | Media, accordion, anchors, FAQ | CMS-driven or highly interactive content | 3 | 6 | 12
Foundation & Layout | UI | Localisation (i18n) | per application | One extra language, static strings | Runtime language switch, locale date/number formats | RTL support, pluralisation, per-user locale persistence | 6 | 12 | 24
Data Display | UI | Data table | per table | Static columns, one API, loaded on page load, no interaction | Server-side sort / filter / pagination, formatted columns | Live updates (polling/websocket), virtualisation, column configuration, inline actions | 4 | 12 | 24
Data Display | UI | Row actions & bulk selection | per table | Edit/delete icons per row | Row selection, bulk action menu, confirmation | Permission-driven actions, async batch operations with progress | 4 | 8 | 16
Data Display | UI | Editable data grid | per grid | Inline edit of one field type | Several editor types, per-cell validation | Spreadsheet-style editing, bulk edit, undo, autosave, large data sets | 12 | 20 | 36
Data Display | UI | Tree / hierarchy view | per view | Static expandable tree | Lazy-loaded nodes, selection | Drag-and-drop, checkboxes, search, inline edit | 8 | 16 | 28
Data Display | UI | Info / record card | per card type | Static content card | Clickable card with states and actions | Inline edit, expandable sections, drag support | 2 | 5 | 10
Data Display | UI | KPI / stat card | per card | Single metric value | Metric with trend and period comparison | Live-updating, thresholds, drill-down | 3 | 6 | 12
Data Display | UI | Detail / summary panel | per panel | Read-only key-value block | Grouped sections with actions, API-fed | Inline edit, conditional sections, permission-aware fields | 3 | 8 | 16
Data Display | UI | Timeline / activity feed | per feed | Static list of events | Icons, metadata, API-fed, paginated | Real-time updates, grouping, filters, expandable detail | 6 | 12 | 20
Data Display | UI | Kanban board | per board | Fixed columns, local drag-and-drop | Changes persisted via API, card detail modal | Swimlanes, WIP limits, real-time sync, permissions | 16 | 28 | 40
Data Display | UI | Empty, loading & error states | per page | Spinner and generic empty message | Skeleton loaders, retry on error | Contextual errors, offline handling, partial-failure UI | 2 | 4 | 8
Forms & Inputs | UI | Form (create / edit) | per form | Up to 5 basic fields, required-field validation, one submit API | 6-12 fields, mixed input types, schema validation, server-error mapping | More than 12 fields, conditional/dependent fields, autosave/draft, unsaved-changes guard | 6 | 14 | 28
Forms & Inputs | UI | Multi-step wizard | per wizard | 2-3 linear steps, local state | 4-5 steps, per-step validation, review step | Branching steps, save/resume, per-step API calls | 12 | 24 | 40
Forms & Inputs | UI | Select / dropdown / combobox | per control type | Static options | Searchable, options loaded from an API | Async search, multi-select, cascading or creatable options | 2 | 6 | 14
Forms & Inputs | UI | Date / date-range picker | per control type | Component-library date picker | Date range, presets, timezone/format handling | Constraints, custom calendar rules, localisation | 3 | 8 | 16
Forms & Inputs | UI | Rich text / markdown editor | per editor | Library drop-in editor | Toolbar, live preview, sanitisation | Mentions, embedded media, collaboration hooks | 6 | 14 | 28
Forms & Inputs | UI | File upload | per control | Single file, basic validation | Multiple files, drag-and-drop, progress bar | Chunked/resumable upload, previews, per-file error handling | 4 | 12 | 24
Search & Filter | UI | Search box & suggestions | per control | Debounced search box | Type-ahead suggestions | Federated results, recent/saved searches, keyboard navigation | 3 | 10 | 20
Search & Filter | UI | Filter bar / panel | per page | 2-3 client-side filters | Multiple filters, chips, API-driven, state kept in URL | Advanced operators, saved filters, nested groups | 4 | 12 | 24
Charts & Dashboards | UI | Standard chart (bar, line, area, pie) | per chart | Single series, one API or static data, default tooltip | Multiple series, legend toggle, axis formatting | Dual-axis / combo, annotations, zoom, real-time updates | 4 | 10 | 20
Charts & Dashboards | UI | Specialised chart (funnel, gauge, heatmap, scatter) | per chart | Library default, single data set | Custom styling, thresholds, interactions | Custom rendering, large data, linked charts | 6 | 14 | 28
Charts & Dashboards | UI | Dashboard layout & global filters | per dashboard | Fixed widget grid | Responsive grid with shared date/filter state | User-customisable widgets (drag, resize, saved layouts) | 6 | 14 | 32
Charts & Dashboards | UI | Pivot / cross-tab table | per table | Fixed aggregation | User-selectable dimensions | Drag-to-configure, subtotals, drill-down | 12 | 24 | 40
Charts & Dashboards | UI | Drill-down interaction | per interaction | Click opens a detail modal | Click navigates to a page with context | Multi-level drill with breadcrumb trail | 4 | 10 | 20
Overlays & Feedback | UI | Modal / dialog | per dialog | Confirm or info message | Content or form with loading/error states | Nested or multi-step dialog | 2 | 5 | 12
Overlays & Feedback | UI | Drawer / side panel | per panel | Static content | Form or detail view backed by an API | Resizable, nested, stateful panel | 3 | 8 | 16
Overlays & Feedback | UI | Toast, alert & banner notifications | per application | Basic toasts | Variants, queue, auto-dismiss | Notification centre with persistence | 2 | 5 | 12
Overlays & Feedback | UI | Progress & job status | per feature | Spinner or progress bar | Polled job status | Real-time progress with cancel and retry | 3 | 8 | 16
AI & Conversational UI | UI | Chat interface | per chat | Message list + input, request/response (no streaming) | Streaming responses, markdown rendering, history, typing indicator | Attachments, tool-call display, multi-session, feedback | 16 | 30 | 48
AI & Conversational UI | UI | Citations & sources panel | per panel | List of source links | Source cards with previews | Inline citation linking, highlight in source document | 4 | 10 | 20
AI & Conversational UI | UI | Agent run / tool-call timeline | per view | Static step list | Live step status | Expandable inputs/outputs, retry, step-level actions | 8 | 16 | 28
AI & Conversational UI | UI | Human-in-the-loop approval | per flow | Approve / reject buttons | Comments and audit trail | Multi-approver, escalation, diff view | 6 | 14 | 24
AI & Conversational UI | UI | AI feedback & suggested prompts | per feature | Static prompt chips | Thumbs up/down with reason, dynamic prompts | Feedback analytics hooks, personalised suggestions | 3 | 8 | 14
AI & Conversational UI | UI | AI structured-output renderer | per renderer | Renders one fixed JSON shape | Several shapes (cards, tables) | Dynamic schema-driven rendering with interactivity | 8 | 16 | 28
Files & Reporting | UI | Data export (CSV / Excel) | per export | Client-side CSV | Formatted Excel, server-triggered | Large asynchronous export with status and download list | 4 | 10 | 20
Files & Reporting | UI | PDF / printable report | per report | Print-friendly stylesheet | Templated PDF export | Multi-section branded report with charts | 8 | 20 | 40
Files & Reporting | UI | Document / file viewer | per viewer | Single image or file preview | PDF/image viewer with zoom and paging | Multi-format, annotations, large files | 6 | 12 | 24
Auth & Access | UI | Login screen | per application | Username/password form, token handling | Adds SSO redirect, remember-me, error states | MFA, multiple identity providers, lockout flows | 6 | 12 | 24
Auth & Access | UI | Password reset & account flows | per application | Reset request form | Reset, verify and change-password flow | Invite, MFA enrolment, account recovery | 6 | 12 | 20
Auth & Access | UI | Role-based UI rendering | per application | Single role guard | Multiple roles, permission-driven menus and buttons | Fine-grained dynamic permissions | 4 | 12 | 24
Auth & Access | UI | Session handling | per application | Logout on expiry | Token refresh, timeout warning | Multi-tab sync, silent re-authentication | 4 | 8 | 16
Admin & Enterprise | UI | User & role management | per module | List users, assign a role | Invite, deactivate, search, assign roles | Bulk operations, delegated administration, audit hooks | 12 | 24 | 40
Admin & Enterprise | UI | Role & permission editor | per editor | Role list with checkboxes | Grouped permissions | Matrix or tree editor with inheritance | 12 | 20 | 32
Admin & Enterprise | UI | Audit log viewer | per viewer | Read-only list | Filter by user / date / action | Change diff view, export, large volumes | 6 | 12 | 24
Admin & Enterprise | UI | Settings / preferences panel | per panel | A few toggles | Grouped settings forms saved via API | Per-tenant/user scoping, dependent validation | 6 | 14 | 24
Backend API | API | CRUD endpoint | per endpoint | Single entity, basic validation | Related entities, business-rule validation | Complex rules, transactions, versioning | 4 | 8 | 16
Backend API | API | List / search endpoint | per endpoint | Pagination only | Filter, sort, pagination, search | Full-text search, dynamic filters, aggregations | 4 | 10 | 20
Backend API | API | Aggregation / analytics endpoint | per endpoint | One simple aggregate | Multiple groupings and filters | Multi-source, time-series, caching | 8 | 16 | 32
Backend API | API | Authentication endpoint | per service | Credentials login + token issue | Refresh, logout, SSO callback | Multiple identity providers, MFA | 8 | 16 | 32
Backend API | API | Authorisation / RBAC layer | per service | Single role check | Role-based route guards | Fine-grained policy engine | 6 | 14 | 28
Backend API | API | File upload / download endpoint | per endpoint | Single small file | Multiple files, validation, storage | Large/chunked files, scanning, signed URLs | 6 | 12 | 24
Backend API | API | External system integration endpoint | per integration | One REST call, no retry | Authentication, data mapping, retry | Multiple dependent calls, async handling, idempotency | 8 | 16 | 32
Backend API | API | Real-time endpoint (SSE / WebSocket) | per endpoint | One-way updates | Two-way messaging, reconnect handling | Fan-out, authentication, back-pressure | 8 | 16 | 28
Backend API | API | Export / report endpoint | per endpoint | Simple CSV | Excel or PDF output | Large asynchronous job | 6 | 14 | 28
Backend API | API | Agent / LLM-facing endpoint | per endpoint | Pass-through request/response to an existing agent | Streaming, session context | Multi-step orchestration, tool-call events | 8 | 16 | 32

## Page Templates
Page Templates
Typical effort for a whole page type at Simple / Medium / Complex level. Hours roll up from 'Page Bundles' and the Component Catalogue. Use these when the RFP only tells you the number and type of pages.
[6 empty] | Hours per page (without AI) |  |  | Components that make up the page (as delivered - Page Bundles is the live source)
Page type | What it covers | Typical API endpoints needed | Simple page = | Medium page = | Complex page = | Simple | Medium | Complex | Simple page components | Medium page components | Complex page components
Login & authentication page | Sign-in screen and account flows | 1-3 (auth, token, reset) | Login form only | Login with SSO redirect, reset link, error states | MFA, multiple identity providers, lockout flows |  |  |  | Login screen (Simple) | Login screen (Medium) Password reset & account flows (Simple) Session handling (Simple) | Login screen (Complex) Password reset & account flows (Medium) Session handling (Medium)
Dashboard / analytics page | KPI cards, charts and supporting tables | 2-6 (aggregation, list) | Up to 4 KPIs and 1-2 basic charts, static filters | 3-5 charts, shared date filter, one detail table | 6+ charts, drill-down, live data, multiple data sources |  |  |  | Dashboard layout & global filters (Simple) 4 x KPI / stat card (Simple) 2 x Standard chart (bar, line, area, pie) (Simple) Empty, loading & error states (Simple) | Dashboard layout & global filters (Medium) 4 x KPI / stat card (Simple) 4 x Standard chart (bar, line, area, pie) (Medium) Data table (Simple) Empty, loading & error states (Medium) | Dashboard layout & global filters (Complex) 6 x KPI / stat card (Medium) 6 x Standard chart (bar, line, area, pie) (Complex) 2 x Specialised chart (funnel, gauge, heatmap, scatter) (Medium) Data table (Medium) 2 x Drill-down interaction (Medium) Empty, loading & error states (Medium)
List / search page | Table with filters and actions | 1-3 (list, search, export) | One read-only table with 2-3 filters | Server-side table with filters, row actions, export | Bulk actions, advanced filters, live updates, saved views |  |  |  | Data table (Simple) Filter bar / panel (Simple) Empty, loading & error states (Simple) | Data table (Medium) Filter bar / panel (Medium) Search box & suggestions (Simple) Row actions & bulk selection (Medium) Data export (CSV / Excel) (Simple) Empty, loading & error states (Medium) | Data table (Complex) Filter bar / panel (Complex) Search box & suggestions (Medium) Row actions & bulk selection (Complex) Data export (CSV / Excel) (Medium) Empty, loading & error states (Medium)
Detail / record page | Summary, tabs, related data and activity | 2-5 (read, update, related lists) | Read-only summary, no tabs | Tabs, a related table, edit action | Inline edit, several related sections, activity timeline, permissions |  |  |  | Detail / summary panel (Simple) Empty, loading & error states (Simple) | Detail / summary panel (Medium) Breadcrumbs & tabs (Medium) Data table (Simple) Timeline / activity feed (Simple) Modal / dialog (Simple) Empty, loading & error states (Medium) | Detail / summary panel (Complex) Breadcrumbs & tabs (Complex) 2 x Data table (Medium) Timeline / activity feed (Medium) 2 x Modal / dialog (Medium) Empty, loading & error states (Medium)
Form / data-entry page | Create or edit a record | 1-3 (create, update, lookups) | One form of up to 5 fields | 6-12 fields, validation, file attachment | Conditional sections, autosave, many field types |  |  |  | Form (create / edit) (Simple) Select / dropdown / combobox (Simple) Empty, loading & error states (Simple) | Form (create / edit) (Medium) 3 x Select / dropdown / combobox (Simple) Date / date-range picker (Simple) File upload (Simple) Empty, loading & error states (Medium) | Form (create / edit) (Complex) 6 x Select / dropdown / combobox (Medium) 2 x Date / date-range picker (Medium) File upload (Medium) Empty, loading & error states (Medium)
Wizard / guided workflow page | Step-by-step process | 2-6 (per-step save, lookups, submit) | 2-3 linear steps | 4-5 steps with review step | Branching steps, save/resume, approvals |  |  |  | Multi-step wizard (Simple) 2 x Select / dropdown / combobox (Simple) Modal / dialog (Simple) Empty, loading & error states (Simple) | Multi-step wizard (Medium) 4 x Select / dropdown / combobox (Simple) Date / date-range picker (Simple) Modal / dialog (Simple) Empty, loading & error states (Medium) | Multi-step wizard (Complex) 6 x Select / dropdown / combobox (Medium) 2 x Date / date-range picker (Medium) 2 x Modal / dialog (Medium) Empty, loading & error states (Medium)
Admin / configuration page | User, role and settings management | 3-8 (users, roles, settings, audit) | A single settings form or user list | User management, roles and audit log | Permission matrix, bulk operations, delegated admin |  |  |  | User & role management (Simple) Data table (Simple) Settings / preferences panel (Simple) Modal / dialog (Simple) Empty, loading & error states (Simple) | User & role management (Medium) Data table (Medium) Settings / preferences panel (Medium) Role & permission editor (Simple) Audit log viewer (Simple) 2 x Modal / dialog (Simple) Empty, loading & error states (Medium) | User & role management (Complex) Data table (Complex) Settings / preferences panel (Complex) Role & permission editor (Medium) Audit log viewer (Medium) 3 x Modal / dialog (Medium) Empty, loading & error states (Medium)
AI chat assistant page | Conversational interface to an agent | 2-5 (chat, history, feedback, stream) | Single-thread request/response chat | Streaming, markdown, conversation history, citations | Attachments, tool-call display, multi-session, structured output |  |  |  | Chat interface (Simple) Empty, loading & error states (Simple) | Chat interface (Medium) Master-detail view (Simple) Citations & sources panel (Simple) AI feedback & suggested prompts (Simple) Empty, loading & error states (Medium) | Chat interface (Complex) Master-detail view (Medium) Citations & sources panel (Medium) AI feedback & suggested prompts (Medium) AI structured-output renderer (Medium) Empty, loading & error states (Medium)
Agent / workflow monitor page | Run list, run detail and approvals | 3-8 (runs, steps, approvals, status) | Run list with status | Live run detail with step timeline | Approvals, retries, drill-down, multi-agent view |  |  |  | Data table (Simple) Detail / summary panel (Simple) Agent run / tool-call timeline (Simple) Empty, loading & error states (Simple) | Data table (Medium) Detail / summary panel (Medium) Agent run / tool-call timeline (Medium) Human-in-the-loop approval (Simple) Progress & job status (Simple) Filter bar / panel (Simple) Empty, loading & error states (Medium) | Data table (Complex) Detail / summary panel (Complex) Agent run / tool-call timeline (Complex) Human-in-the-loop approval (Medium) Progress & job status (Medium) Filter bar / panel (Medium) Empty, loading & error states (Medium)
Report & export page | Filtered report with downloads | 2-5 (query, aggregate, export) | Single table report with CSV export | Filters, charts, Excel/PDF export | Multi-section branded report, asynchronous generation |  |  |  | Filter bar / panel (Simple) Data table (Simple) Data export (CSV / Excel) (Simple) Empty, loading & error states (Simple) | Filter bar / panel (Medium) Data table (Medium) 2 x Standard chart (bar, line, area, pie) (Simple) Data export (CSV / Excel) (Medium) PDF / printable report (Medium) Empty, loading & error states (Medium) | Filter bar / panel (Complex) Data table (Complex) 4 x Standard chart (bar, line, area, pie) (Medium) Data export (CSV / Excel) (Complex) PDF / printable report (Complex) Empty, loading & error states (Medium)
Content / landing page | Static or lightly interactive content | 0-1 | Text and images | Sections, accordion, anchors | Highly interactive or CMS-driven content |  |  |  | 2 x Static content section (Simple) Responsive layout (Simple) | 4 x Static content section (Medium) Responsive layout (Medium) | 6 x Static content section (Medium) Responsive layout (Complex)
Page hours cover the page's own components only. Add shared items once per application (app shell, navigation, theme, role-based rendering, session handling) in Section B of the Estimator, and the back-end APIs in Section C. 'Typical API endpoints' is a guide for choosing API counts.

## Page Bundles
Page Bundles (detail behind Page Templates)
Which catalogue components make up each page type at Simple / Medium / Complex page level. Quantity 0 = component not in that page level. Edit quantities and levels to tune a template.
|  | Quantity per page |  |  | Complexity of component |  |  | Hours (without AI) |  |  | Helper keys (do not edit) - used by the Estimator's Page Explorer. Copy down when adding rows.
Page type | Component | Simple page | Medium page | Complex page | Simple page | Medium page | Complex page | Simple page | Medium page | Complex page | Simple key | Medium key | Complex key
Login & authentication page | Login screen | 1 | 1 | 1 | Simple | Medium | Complex
Login & authentication page | Password reset & account flows | 0 | 1 | 1 | - | Simple | Medium
Login & authentication page | Session handling | 0 | 1 | 1 | - | Simple | Medium
Dashboard / analytics page | Dashboard layout & global filters | 1 | 1 | 1 | Simple | Medium | Complex
Dashboard / analytics page | KPI / stat card | 4 | 4 | 6 | Simple | Simple | Medium
Dashboard / analytics page | Standard chart (bar, line, area, pie) | 2 | 4 | 6 | Simple | Medium | Complex
Dashboard / analytics page | Specialised chart (funnel, gauge, heatmap, scatter) | 0 | 0 | 2 | - | - | Medium
Dashboard / analytics page | Data table | 0 | 1 | 1 | - | Simple | Medium
Dashboard / analytics page | Drill-down interaction | 0 | 0 | 2 | - | - | Medium
Dashboard / analytics page | Empty, loading & error states | 1 | 1 | 1 | Simple | Medium | Medium
List / search page | Data table | 1 | 1 | 1 | Simple | Medium | Complex
List / search page | Filter bar / panel | 1 | 1 | 1 | Simple | Medium | Complex
List / search page | Search box & suggestions | 0 | 1 | 1 | - | Simple | Medium
List / search page | Row actions & bulk selection | 0 | 1 | 1 | - | Medium | Complex
List / search page | Data export (CSV / Excel) | 0 | 1 | 1 | - | Simple | Medium
List / search page | Empty, loading & error states | 1 | 1 | 1 | Simple | Medium | Medium
Detail / record page | Detail / summary panel | 1 | 1 | 1 | Simple | Medium | Complex
Detail / record page | Breadcrumbs & tabs | 0 | 1 | 1 | - | Medium | Complex
Detail / record page | Data table | 0 | 1 | 2 | - | Simple | Medium
Detail / record page | Timeline / activity feed | 0 | 1 | 1 | - | Simple | Medium
Detail / record page | Modal / dialog | 0 | 1 | 2 | - | Simple | Medium
Detail / record page | Empty, loading & error states | 1 | 1 | 1 | Simple | Medium | Medium
Form / data-entry page | Form (create / edit) | 1 | 1 | 1 | Simple | Medium | Complex
Form / data-entry page | Select / dropdown / combobox | 1 | 3 | 6 | Simple | Simple | Medium
Form / data-entry page | Date / date-range picker | 0 | 1 | 2 | - | Simple | Medium
Form / data-entry page | File upload | 0 | 1 | 1 | - | Simple | Medium
Form / data-entry page | Empty, loading & error states | 1 | 1 | 1 | Simple | Medium | Medium
Wizard / guided workflow page | Multi-step wizard | 1 | 1 | 1 | Simple | Medium | Complex
Wizard / guided workflow page | Select / dropdown / combobox | 2 | 4 | 6 | Simple | Simple | Medium
Wizard / guided workflow page | Date / date-range picker | 0 | 1 | 2 | - | Simple | Medium
Wizard / guided workflow page | Modal / dialog | 1 | 1 | 2 | Simple | Simple | Medium
Wizard / guided workflow page | Empty, loading & error states | 1 | 1 | 1 | Simple | Medium | Medium
Admin / configuration page | User & role management | 1 | 1 | 1 | Simple | Medium | Complex
Admin / configuration page | Data table | 1 | 1 | 1 | Simple | Medium | Complex
Admin / configuration page | Settings / preferences panel | 1 | 1 | 1 | Simple | Medium | Complex
Admin / configuration page | Role & permission editor | 0 | 1 | 1 | - | Simple | Medium
Admin / configuration page | Audit log viewer | 0 | 1 | 1 | - | Simple | Medium
Admin / configuration page | Modal / dialog | 1 | 2 | 3 | Simple | Simple | Medium
Admin / configuration page | Empty, loading & error states | 1 | 1 | 1 | Simple | Medium | Medium
AI chat assistant page | Chat interface | 1 | 1 | 1 | Simple | Medium | Complex
AI chat assistant page | Master-detail view | 0 | 1 | 1 | - | Simple | Medium
AI chat assistant page | Citations & sources panel | 0 | 1 | 1 | - | Simple | Medium
AI chat assistant page | AI feedback & suggested prompts | 0 | 1 | 1 | - | Simple | Medium
AI chat assistant page | AI structured-output renderer | 0 | 0 | 1 | - | - | Medium
AI chat assistant page | Empty, loading & error states | 1 | 1 | 1 | Simple | Medium | Medium
Agent / workflow monitor page | Data table | 1 | 1 | 1 | Simple | Medium | Complex
Agent / workflow monitor page | Detail / summary panel | 1 | 1 | 1 | Simple | Medium | Complex
Agent / workflow monitor page | Agent run / tool-call timeline | 1 | 1 | 1 | Simple | Medium | Complex
Agent / workflow monitor page | Human-in-the-loop approval | 0 | 1 | 1 | - | Simple | Medium
Agent / workflow monitor page | Progress & job status | 0 | 1 | 1 | - | Simple | Medium
Agent / workflow monitor page | Filter bar / panel | 0 | 1 | 1 | - | Simple | Medium
Agent / workflow monitor page | Empty, loading & error states | 1 | 1 | 1 | Simple | Medium | Medium
Report & export page | Filter bar / panel | 1 | 1 | 1 | Simple | Medium | Complex
Report & export page | Data table | 1 | 1 | 1 | Simple | Medium | Complex
Report & export page | Standard chart (bar, line, area, pie) | 0 | 2 | 4 | - | Simple | Medium
Report & export page | Data export (CSV / Excel) | 1 | 1 | 1 | Simple | Medium | Complex
Report & export page | PDF / printable report | 0 | 1 | 1 | - | Medium | Complex
Report & export page | Empty, loading & error states | 1 | 1 | 1 | Simple | Medium | Medium
Content / landing page | Static content section | 2 | 4 | 6 | Simple | Medium | Medium
Content / landing page | Responsive layout | 1 | 1 | 1 | Simple | Medium | Complex

## Assumptions
Assumptions & Calibration
Editable parameters used across the workbook. Blue text on yellow = input.
Parameter | Value | Notes
AI-assist effort reduction | 30% | PLACEHOLDER. Share of effort saved when developers use an AI coding assistant (e.g. Copilot). To be replaced with a figure validated by delivery teams.
Technology factor | 1 | Multiplier on total effort. 1.00 = baseline stack (Next.js/React + TypeScript + a component library). Raise it for stacks that need more hand-built UI (e.g. 1.25 if most components are built by hand).
Hours per person-day | 8 | Used to convert hours into person-days.
Productive hours per person-week | 40 | Used only for the indicative duration on the Estimator sheet.
Baseline assumptions behind the hours
What the hours cover | Developer effort to build the component AND write its unit tests, for a typical first implementation.
What the hours exclude | UAT, integration/system testing, project management, requirements gathering, DevOps/infrastructure, database design and data pipelines.
Who does the work | An average Kyndryl developer. Hours are generic, not person-specific.
Platform | Modern web applications only. No mobile apps, desktop apps or legacy server-rendered stacks.
Front-end baseline | Next.js / React with TypeScript and an established component library (e.g. MUI, Ant Design, shadcn/ui). Approved designs are available before build starts.
Back-end baseline | REST APIs (e.g. Python/FastAPI or Node). Includes routing, validation, business logic, error handling, unit tests and API documentation. Data is accessed through APIs, not direct database connections.
Agent / AI back-end | Agent, pipeline and RAG development is NOT estimated here. Only the UI and API layer that talk to agents are covered.
Hours status | DRAFT starting values. Team members enter their own experience-based hours here. Hours must be generic, i.e. deliverable by any Kyndryl developer, not person-specific.
Calibration log (optional - record delivered projects to refine the hours)
Project / scope summary | Estimated hrs | Actual hrs | Variance % | Lessons / reason